Scope of Work (SoW) Document

# ModelOps Proof of Concept (PoC)

# Phases, Tasks, and Timeline

| Phase | Tasks | Timeline (Weeks) |
| --- | --- | --- |
| 1. Requirements & Approach Validation | - Onboarding - Evaluate Use Case #1 (source data architecture & data model) | Week 1 |
| 2. Teradata SME Knowledge Transfer & ETL Flow Evaluation | - Assess Vantage as analytic dataset repository - Vantage education & data migration guidance (ADS integration with ModelOps) *Assumes ADS exists; no custom feature engineering or transformation | Weeks 1–2 |
| 3. ModelOps Installation & Knowledge Transfer | - Install ModelOps - Configure ModelOps for Use Case #1 (medium complexity or as-is migration) - ModelOps knowledge transfer - Setup: Keycloak, Git integration, PyPI local mirror (if needed) | Weeks 1–3 |
| 4. Use Case #1 Refinement, Validation & Deployment | - Evaluate data prep & data model - Guidance on model training & execution (Teradata DS + e& SME) - Deploy model to ModelOps | Weeks 3–5 |
| Deliverables | - Insert Use Case #1 model into ModelOps - Support for data prep, connecting pipelines in Vantage, and model training | By Week 5 |

# Assumptions

ADS (Analytic Dataset) already exists; no custom feature engineering or data transformation required.

e& provides access to source data architecture and data model for Use Case #1, and Git environment for integration.

e& resources available: SMEs for data/model validation and data scientists for training guidance.

Infrastructure readiness: Vantage environment installed and accessible; network connectivity for ModelOps installation.

# Dependencies

e& IT team for Keycloak setup, Git integration, and DevPi (PyPI mirror) setup if needed.

Data availability: Source data for Use Case #1 must be complete and accessible.

Model readiness: Existing model for migration or deployment (no new model development).

Teradata SME support for Vantage education, migration guidance, and ModelOps configuration.

# Risks

Data quality issues could delay validation and deployment.

Infrastructure delays (e.g., Vantage or ModelOps installation) may impact timeline.

Limited e& SME availability could slow down knowledge transfer and model refinement.

Integration challenges with e& Git or Keycloak environment.

Scope creep if new use cases or e& feature engineering are requested (explicitly out-of-scope).